ANEX III: Technical Offer

“Technical assistance for the development and implementation of Capacity Building and Coaching for FSTP Beneficiaries (May–December 2025) - YOU(th) CARE”.

|  | Activity | Estimated Number of Days |
| --- | --- | --- |
| 1st phase: CAPACITY BUILDING (with potential beneficiaries) | 1.Design of workshop/s + elaboration of the timeline/agenda and elaboration of the materials 2. Facilitation of workshop/s 3. Elaboration of the final report on capacity building | Before end of May 2025 (2 days) Before mid of June 2025 (8 days) Before end of June 2025 (3 days) |
| 2nd phase: COACHING (with selected beneficiaries) | 1.Design of workshop 2 + elaboration of the timeline/agenda and elaboration of the materials 2.Facilitation of coaching sessions 3. Elaboration of the final report on Coaching | Before end of September 2025 (2 days) Before end of November 2025 (15 days) Before mid December 2025 (2 days) |
|  | TOTAL: | 32 days |

Date:

Signature: